## Task List
Project Requirements
Task | Details | Assigned To | Date Due | Completed By
Use Cases |  | Tyler Crouch | 2024-07-01 | Tyler Crouch
2 Player Game, after start
Join Up nd Game Creation with 2 players
User Interface |  | Noe Sanchez | 2024-07-01 | Noe Sanchez
"Lobby"
"Game"
"Results"
"LeaderBoard / Statistics"
System Requirements |  | Ravi Ray | 2024-07-01 | Ravi Ray
"Lobby"
"Game"
"Results"
"LeaderBoard / Statistics"
|  | Logan Wells | 2024-07-01 | Logan Wells
Unknown List
Review for consistency and completeness
Project Design
Task | Details | Assigned To | Date Due | Completed By
Set Up Github Repositoty | Invite |  | 2024-07-19
Branch for Initial Design
Classs Diagram | Class Player |  | 2024-07-19
Class UI Inretface
Class Websockets
Class Server
Class game
Class wordsource
Source Code | Implement class Player |  | 2024-07-19
Implement class UI Interface
Implement class Websockets
Implement class Server
Implement class
Implement class
Implement class
Implement class
Requirements | Make requirements for Player class |  | 2024-07-19

## TBD LIST
ID | DESCRIPTION | RATIONALE | STATUS / RESOLUTION IDEAS
TBD1 | Procedures for handling player disconnections and reconnections. | To maintain game integrity and player experience, need to determine cases of if a player disconnects after the game has began and also if they were to recconct after that. Would they be allowed to reenter; would their data still be stored? | * Use a grace period to time before they are diconnected and let them know of this when game starts? *Or terminate their score and data upon leaving the session? (If there are only two players the game would need to terminate as well). *Or let them rejoin seamlessly whenever, their turns will be fofeited for as long as they are not in the session, if they rejoin after the game has ended they will be presented with a message showing the final scores fo the session and the winner.
TBD2 | Specific rules for determining winner in case of a tie after additional rounds. | Clarification needed to handle edge cases and rules for them. Will the additional rounds after a tie be sets of 3 rounds like the original game to make it fair for all players? Then if no winners after that set, then another set and so on? | Unresolved
TBD3 | Handling of imcomplete games. | If all players were to diconnect, or if 2 of 4 players dicconect before the game ends does the game still continue for the players remaining in the session? If so, say 1 of the disconnected players has a higher score than the the players still in the session, does the dicsonnected player win or is his data wiped from the scoreboard? Also if all players dicconnect game is over and no winner is determined? | Unresolved
TBD4 | Timing rules for player actions. | Necessary to maintain fairness as well as game pace. Will we equally time players like in the WOF game? Or leave timing to the players? If so what method will be used? | Unresolved

## Requirements
UID | F/NF | Description | From/Source | Rationale
TOD-REQ01 | NF | The game shall be playable with 2, 3, or 4 players. | Project Description | Ensures flexibility in gameplay to accommodate different numbers of players.
TOD-REQ02 | NF | The system shall allow multiple "Turn of Destiny" games to be played simultaneously on the same server. | Project Description | Enables scalability and efficient use of server resources.
TOD-REQ03 | F | When a player loads the web page, the system shall provide a way to wait for additional players to join. | Project Description | Enhances user experience by managing player waiting time effectively.
TOD-REQ04 | F | The system shall allow the game to start after the second, third, or fourth player joins. | Project Description | Ensures the game can commence once the minimum number of players are present.
TOD-REQ05 | NF | The game shall be turn-based. | Project Description | Defines the core gameplay mechanic.
TOD-REQ06 | F | The system shall select either one, two, or three words at random from a data file of valid words. | Project Description | Adds variability and challenge to the game.
TOD-REQ07 | F | Each word shall be displayed as 'empty cells' to all players, with spaces between words shown. | Project Description | Clarifies word display format for players.
TOD-REQ08 | F | The first player to act in a round shall select a button called "Play." | Project Description | Standardizes the starting action for each round.
TOD-REQ09 | F | Upon selecting "Play," the game shall select one of 20 possible stakes for the player to win on that turn. | Project Description | Introduces a random reward mechanism to increase excitement.
TOD-REQ10 | F | The system shall display the selected stake to all players, even when it is not their turn. | Project Description | Keeps all players informed and engaged.
TOD-REQ11 | F | The active player shall decide on an action: solve the puzzle, buy vowels, or select a consonant. | Project Description | Provides clear options for player actions during their turn.
TOD-REQ12 | F | If a player identifies a vowel or consonant, it shall be displayed to all players. | Project Description | Ensures transparency and visibility of game progress.
TOD-REQ13 | F | The player shall receive the value of the stake for each identified letter, added to their score. | Project Description | Rewards player actions with points.
TOD-REQ14 | F | Players shall take turns in order. | Project Description | Ensures orderly gameplay.
TOD-REQ15 | F | When a player identifies all words, the round shall end. | Project Description | Defines the end condition for each round.
TOD-REQ16 | F | A game shall consist of 3 rounds. | Project Description | Establishes the structure of a complete game.
TOD-REQ17 | F | At the end of 3 rounds, the player with the largest balance shall be the winner. | Project Description | Determines the winning condition.
TOD-REQ18 | F | If there is a tie, additional rounds shall be played until there is a winner. | Project Description | Ensures a clear winner is determined.
TOD-REQ19 | F | The system shall maintain a scoreboard of the highest scoring players from all games played on the server. | Project Description | Provides a competitive element by tracking high scores.
TOD-REQ20 | NF | The game shall be a client-server system. | Project Description | Defines the architectural model.
TOD-REQ21 | NF | The user interface shall be a single HTML page, with an optional CSS file. | Project Description | Specifies the simplicity and consistency of the user interface.
TOD-REQ22 | NF | All game logic shall be contained in the Java program. | Project Description | Centralizes game logic for maintainability and performance.
TOD-REQ23 | NF | Communications between clients and the server shall be via WebSockets. | Project Description | Ensures real-time, bidirectional communication.
TOD-REQ24 | NF | The game shall be hosted on a Linux system. | Project Description | Specifies the operating environment for hosting the game.
TOD-REQ25 | NF | The user interface shall have identifiers for each input and output. | Requirements Specification | Facilitates requirement tracking and validation.
TOD-REQ26 | F | The system shall provide mockups of the user interface. | Requirements Specification | Helps in visualizing and planning the user interface design.
TOD-REQ27 | F | The system shall include use cases for joining and creating a game with 2 players. | Requirements Specification | Provides clarity on user interactions and system responses.
TOD-REQ28 | F | The system shall include use cases for playing a game with 2 players. | Requirements Specification | Defines the flow of gameplay for a minimum player count scenario.
TOD-REQ29 | NF | The system shall maintain a spreadsheet of system requirements. | Requirements Specification | Ensures organized and systematic requirement documentation.
TOD-REQ30 | NF | The spreadsheet shall include columns for F/NF flag, Unique ID, From, Requirement Text, Source, and Rationale. | Requirements Specification | Standardizes requirement documentation for clarity and traceability.
TOD-REQ31 | NF | The system shall include a list of unknown or TBD items in an additional tab of the requirements spreadsheet. | Requirements Specification | Manages and tracks ambiguous or unresolved issues.
TOD-REQ32 | F | The system shall display the player's score prominently during gameplay. | User Interface | Keeps players informed of their progress and current standing.
TOD-REQ33 | F | The game shall display a timer showing the time elapsed in each round. | User Interface | Adds time pressure and enhances engagement.
TOD-REQ34 | F | The game shall display the current turn's active player. | User Interface | Clearly indicates whose turn it is to all players.
TOD-REQ35 | F | The system shall provide a "Forfeit" button for players who wish to quit the game. | User Interface | Allows players to exit the game if they choose to.
TOD-REQ36 | F | If a player forfeits, the system shall grant the remaining players a win. | User Interface | Ensures fair play and adjusts the game state accordingly.
TOD-REQ37 | F | The system shall deduct a significant penalty from a player's score if they forfeit. | User Interface | Discourages players from quitting the game prematurely.
TOD-REQ38 | NF | The system shall generate a new word puzzle in less than 2 seconds. | Performance Requirement | Ensures a responsive and smooth gameplay experience.
TOD-REQ39 | F | The system shall display the correct word puzzle once it is solved. | User Interface | Confirms the correct solution to all players.
TOD-REQ40 | NF | The system shall log all player actions for audit and analysis purposes. | Logging and Monitoring | Provides a record of gameplay for troubleshooting and performance analysis.
TOD-REQ41 | F | The system shall provide a chat feature for players to communicate during the game. | User Interface | Enhances player interaction and social engagement.
TOD-REQ42 | F | The chat feature shall allow toggling between global and local game chat. | User Interface | Provides flexibility in communication options.
TOD-REQ43 | F | The system shall save the current game state in case of server issues or disconnections. | Reliability Requirement | Ensures game continuity and resilience.
TOD-REQ44 | F | The system shall allow players to reconnect and resume their game if they lose connection. | Reliability Requirement | Enhances user experience by allowing recovery from disconnections.
TOD-REQ45 | NF | The game shall be accessible on all modern web browsers. | Compatibility Requirement | Ensures broad accessibility for users.
TOD-REQ46 | NF | The system shall use a secure WebSocket connection (wss://) for communication. | Security Requirement | Protects data integrity and confidentiality during communication.
TOD-REQ47 | F | The system shall enforce a turn time limit to keep the game progressing. | Gameplay Mechanic | Maintains game flow and prevents stalling.
TOD-REQ48 | NF | The system shall have automated tests for all major functionalities. | Quality Assurance | Ensures reliability and correctness of the game through continuous testing.
TOD-REQ49 | F | The system shall provide visual and sound effects for key game actions (e.g., correct letter, wrong guess). | User Interface | Enhances user experience through feedback and engagement.
TOD-REQ50 | F | The system shall allow players to view the scoreboard at any time during the game. | User Interface | Provides ongoing motivation and tracking of progress.
TOD-REQ51 |  | The system should always display the Tiltle of the Game at all time | User Interface
TOD-REQ52 |  | The Start screen should show the players that are playing in the current game | User Interface | Provides players to view eachother
TOD-REQ53 |  | The start screen should have a button to start the game | User Interface | Allows players to enter a game when 2 or more palyers join
TOD-REQ54 |  | The rounds screen should have a wheel that sipns and outputs the results of the spin | User Interface | Allows for the players to spin the wheel to get points or to lose a turn
TOD-REQ55 |  | The rounds screen should display the remaing words of the alphabet and should be crossed out when its bought and used | User Interface | Allows to all players to see what remaining word are avalible to buy and use.
TOD-REQ56 |  | The rounds screen should display the chosen letter | User Interface | Allows for all players to see what current word is being used
TOD-REQ57 |  | The rounds screen should have a button that allows for players to buy a letter/vouel | User Interface | Allows for players to the option of selecting a letter to guess and helps progress the game
TOD-REQ58 |  | The rounds screen should have a button that allows for players to solve the word(s) | User Interface | Allows the player to solve the word and would keep the game more entertaining
TOD-REQ59 |  | The rounds screen should have a button that allows for players to end thier turn | User Interface | Alows for the player to end thier turn, could allow players to skip thier turn.
TOD-REQ60 |  | The results screen should display the winner at the top of the rankings | User Interface
TOD-REQ61 |  | the results screen should diaplay the losers below the winner | User Interface
TOD-REQ62 |  | the results screen should have a button that allows the players to play again | User Interface | Allows for the game to be played by the same players to continue.
TOD-REQ63 |  | the results screen should have a button that allows the players to end the game | User Interface | Allows for the game to end so that new players can play.
TOD-REQ64 |  | The rounds screen should display the players | User Interface | Allows for players to see how other players are doing, ensures compettition .