## Task List
Project Requirements
Task | Details | Assigned To | Date Due | Completed By
Use Cases |  | Tyler Crouch | 2024-07-01 | Tyler Crouch
2 Player Game, after start
Join Up nd Game Creation with 2 players
User Interface |  | Noe Sanchez | 2024-07-01 | Noe Sanchez
"Lobby"
"Game"
"Results"
"LeaderBoard / Statistics"
System Requirements |  | Ravi Ray | 2024-07-01 | Ravi Ray
"Lobby"
"Game"
"Results"
"LeaderBoard / Statistics"
|  | Logan Wells | 2024-07-01 | Logan Wells
Unknown List
Review for consistency and completeness
Project Design
Task | Details | Assigned To | Date Due | Completed By
github repository | Invite Team members | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Create branch for Initial Design | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Merge Design Branch | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Set up Repository | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Submitting GitHub Repository | Noe Sanchez | 2024-07-19 | Noe Sanchez
Classs Diagram | Class Player | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Class Websockets | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Class Server | Ravi Ray | 2024-07-19 | Ravi Ray
| Class Scoreboard | Ravi Ray | 2024-07-19 | Ravi Ray
| Class wordsource | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Class WordSelector | Ravi Ray | 2024-07-19 | Ravi Ray
| Class App | Ravi Ray | 2024-07-19 | Ravi Ray
| Class GameServer | Ravi Ray | 2024-07-19 | Ravi Ray
| Class GameState | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Class GameSession | Logan Wells | 2024-07-19 | Logan Wells
| Class GameLogic | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Class HttpServer | Ravi Ray | 2024-07-19 | Ravi Ray
Source Code | ReadMe Description | Logan Wells | 2024-07-19 | Logan Wells
| Implement class Player | Tyler Crouch,Ravi Ray | 2024-07-19 | Tyler Crouch
| Implement class Websockets | Logan Wells | 2024-07-19 | Logan Wells
| Implement class HttpServer | Logan Wells,Ravi Ray | 2024-07-19 | Logan Wells,Ravi Ray
| Implement class GameLogic | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Implement class App | Ravi Ray | 2024-07-19 | Ravi Ray
| Implement class GameServer | Ravi Ray | 2024-07-19 | Ravi Ray
| Implement class GameState | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Implement class WordSelector | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Implement class Scoreboard | Ravi Ray | 2024-07-19 | Ravi Ray
| Implement class GameSession | Logan Wells | 2024-07-19 | Logan Wells
| Implement class WordSource | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Create Main HTMl File | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Set up Initial Js File | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Define Html Structure | Noe Sanchez | 2024-07-19 | Noe Sanchez
| CSS style sections | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Visibillity logic | Noe Sanchez | 2024-07-19 | Noe Sanchez
Requirements | Make requirements for Player class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for Scoreboard class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for Websockets class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for HttpServer class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for GameLogic class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for GameServer class | Ravi Ray | 2024-07-19 | Ravi Ray
| Make requirements for GameState class | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Make requirements for GameSession class | Logan Wells | 2024-07-19 | Logan Wells
| Make requirements for App class | Ravi Ray | 2024-07-19 | Ravi Ray
| Make requirements for WordSource class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for WordSelector class | Tyler Crouch | 2024-07-19 | Tyler Crouch
Project Implementation
Task | Details | Assigned To | Date Due | Completed By
Deployment | Deploying the Website to the server | Noe Sanchez | 2024-07-22 | Noe Sanchez
|  | Ravi Ray |  | Ravi Ray
Implement Source code for each class | GameServer.java | Logan Wells | 2024-07-22 | Logan Wells
| Scoreboard.java | Logan Wells and Ravi Ray | 2024-07-22 | Logan Wells and Ravi Ray
| GameState.java | Tyler Crouch | 2024-07-22 | Tyler Crouch
| Player.java | Tyler Crouch | 2024-07-22 | Tyler Crouch
| app.java | Noe Sanchez | 2024-07-22 | Noe Sanchez
| PlayerType.java | Noe Sanchez | 2024-07-22 | Noe Sanchez
| HttpServer.java | Noe Sanchez and Ravi | 2024-07-22 | Noe Sanchez and Ravi
| WordSource.java | Ravi Ray | 2024-07-22 | Ravi Ray
| GameWebSocket.java | Logan Wells and Noe Sanchez | 2024-07-22 | Logan Wells and Noe Sanchez
| GameLogicTest.java | Noe Sanchez | 2024-07-22 | Noe Sanchez
Unit Test | GameServerTest.java | Logan Wells | 2024-07-22 | Logan Wells
| ScoreboardTest.java | Logan Wells | 2024-07-22 | Logan Wells
| GameStateTest.java | Logan Wells | 2024-07-22 | Logan Wells
| WordSelectorTest.java | Logan Wells | 2024-07-22 | Logan Wells
| PlayerTest.java | Noe Sanchez | 2024-07-22 | Noe Sanchez
| WordSourceTest.java | Ravi Ray | 2024-07-22 | Ravi Ray
| GameLogicTest.java | Noe Sanchez | 2024-07-22 | Noe Sanchez and Ravi
Update Requiremnents | Emailing professor inregards to formating | Noe Sanchez | 2024-07-22 | Noe Sanchez
| Updating the requirements | Noe Sanchez | 2024-07-22 | Noe Sanchez
|  | Logan Wells |  | Logan Wells
|  | Ravi Ray |  | Ravi Ray
|  | Tyler Crouch |  | Tyler Crouch

## Requirements
UID | F/NF | Description | From/Source | Rationale | Implemented by
TOD-REQ01 | F | the system shall allow the retrieval of the players name. | Design Team | to access player information when needed | Player.java -> "getName()
TOD-REQ02 | F | the system shall allow a player to buy a vowel and update the game state accordingly | Stakeholder | To porvide gameplay functionality related to choosing consonants | Player.java -> choose Consonat(char consoncat, List<String> words)
TOD-REQ03 | F | the system shall clear the list of players when the player hits the play again button | Design Team | to rest the game state and start a new game session | Player.java -> clearPlayerLIst()
TOD-REQ04 | F | the system shall retrive the list of players | Design Team | to access and manage the list of players in the gmae | Player.java -> getPlayerLIst()
TOD-REQ05 | F | the system shall assign and manages player orders | Design Team | to determine the order in which players take thier turns | Player.java -> getPlayerOrder(),setPlayerOrder(PlayerType type)
TOD-REQ06 | F | The player name shall be input into the user interface and when the button is pressed the name is storred in the system | Stakeholder | To uniquely identify each player and store thier infomation in the system | Player.java -> Player(String name)
TOD-REQ07 | F | the player id shall be assigned automattically and incremented sequenltially starting from 1. | Design Team | to uniquely identify each player and maintain order | Player.java -> Player(String name)
TOD-REQ08 | F | the system shall allow the removal of a player by thier ID. | Stakeholder | to manage the list of active players and remove any players as needed | Player.java -> removePlayer(int playerId)
TOD-REQ09 | F | the systam shall allow sending a messaged from the player when a player clicks on a button | Stakeholder | To enable communication and interaction within the game | Player.java -> sendMessage (String message
TOD-REQ10 | F | the system shall ensure the player name is unique among all player | Design Team | To prevent duplicate player names and ensure unique ID | Player.java -> verifyName(String PlayerName)
TOD-REQ11 | F | the system shall determine whether a player is currently active | Design Team | to track player progress and update thier scores during the game | Player.java ->getScore(),setScore(int score), addPoints(int points),resetPoints(),updateScore(int score)
TOD-REQ12 | F | the system shall allow updating a players name | Stakeholder | to correct or change player name if necessary | Player.java ->setName(String name)
TOD-REQ13 | F | the system shall allow a player to solve the puzzle and update the game state based on the solutions correctness | Stakeholder | to provide gameplay functionality related to solveing the puzzle | Player.java ->solvePuzzle(List<String> solution,List<String>puzzle
TOD-REQ14 | F | This enum PlayerType shall label number of players (1 - 4) | Enum PlayerType | Allows for easy tracking of players and identifying number of players. | PlayerType
TOD-REQ17 | F | the system shall use "words.txt" as the default file path for reading the hidden words | Design Team | To provide a default souce of words for the game | WordSource -> WordSource()
TOD-REQ18 | F | The system shall allow specifying a custom file path for the word source | Stakeholder | To enable flexability in selecting diffrent word sources | WordSource -> getSource(String filePath)
TOD-REQ19 | F | The system shall read all words from the specified file into a list | Stakeholder | to Load the words into the game for use | WordSource -> readWordsFromFile()
TOD-REQ20 | F | the system shall handle IO exceptions when reading the word file and provide appropriate error message | Design Team | to ensure robustness and provide feedback on error | WordSource -> readWordsFromFile()
TOD-REQ21 | F | The system shall allow retrieval of the list of words read from the file | Design Team | to access the words for sue in the game | WordSource -> getWords()
TOD-REQ22 | F | the system shall select a random word from the list of words | Stakeholder | to randomly choose a word for gameplay purposes | WordSOurce.java ->chooseRandomWord()
TOD-REQ24 | F | The system shall initialize a WordSelector with a given WordSource | Design Team | to allow the WordSelector to sue words from the WorceSource java file | WordSelector.java -> WordSelector(WordSource wordsource)
TOD-REQ25 | F | the system shall select a random word from the list of words proved by WordSource | Stakeholder | to randomly choose a word for gameplay purposes | WordSelector.java -> selectRandomWord()
TOD-REQ26 | F | the system shall return null if the word list is empty or not initialized when selecting a random word | Design Team | to handle cases where no words are abailable or when the sorce for the words is not avaialabe | WordSelector.java -> selectRandomWord()
TOD-REQ27 | F | the system shall selsect three random words from the list of words provided by WordSource | Stakeholder | to randomly choose multiple words for gampley purposes | WordSelector.java -> selectThreeRandomWords
TOD-REQ28 | F | the system shall return an empty list if the words list has fewer than three words when selecting three random words | Design Team | to handle cases when there is not enough words available, or when the word source list holy has one or two words | WordSelector.java -> selectThreeRandomWords
TOD-REQ29 | F | the system shall select three maingful words form the list of words provide by WordSource | Stakeholder | to ensure selected words are meaningful for the game | WordSelector.java -> selectThreeManingfulWords
TOD-REQ30 | F | the system shall return an empty list if the words list has fewer than three words when selecting three meaningful words | Design Team | to handle cases when there is not enough words available, or when the word source list holy has one or two words | WordSelector.java -> selectThreeManingfulWords
TOD-REQ32 | F | the systam shall initalize a scoreboard with an empty schore map | Design Team | to keep track of player scores form the beginning of the game | Scoreboard.java ->Scoreboard()
TOD-REQ33 | F | the system shall update the score for a player, adding to the existing score if the player already has a score | Stakeholder | to accuratley track and update player scores during game session | Scoreboard.java ->updateScore(String PlayerName,int score)
TOD-REQ34 | F | the system shall retrieve the current score for a player | Stakeholder | to display or use the players current score in the game | Scoreboard.java -> getScore(String PlayerName)
TOD-REQ35 | F | the system shall return a score of 0 for a player if the plaer does not have an existing score | Design Team | to handle cases where a players score has not be initialized | Scoreboard.java -> getScore(String PlayerName)
TOD-REQ37 | F | The system shall initialize the game state with default valuesindised the player cards | Design Team | to start the game with a known inital state | GameState.java -> GameState()
TOD-REQ38 | F | the system shall allow retrieving the list of players in the game, and be able to display it inside the players cards | Stakeholder | to access plaer informatin for gamplay and display | GameState.java -> getPlayers()
TOD-REQ39 | F | the system shall allow setting the list of players in the game | Stakeholder | to update player information at the start or during the game | GameState.java -> setPlayers(List<Player> players)
TOD-REQ40 | F | the system shall allow retrieving the current word being guessed and compare it to the wrod that the player is guession when the player clicks on the "solve" button | Stakeholder | to compare the current word to the guessed word to see if they are the same or not to determing if guess is correct | GameState.java ->getCurrentWord()
TOD-REQ41 | F | the system shall allow setting the current word being guessed when the game moves on to the next round | Stakeholder | to update the current word at the start of a new round | GameState.java -> setCurrentWord(String currentWord)
TOD-REQ42 | F | the system shall allow retrieving the list of guessed letters, once the player hist submit on the "buy Letter" button | Stakeholder | to access guessed letter and cross refrences them with the current letter | GameState.java -> getGuessedLetters()
TOD-REQ43 | F | the system shall allow retriving the current round number, after every round so that it can update to all players | Stakeholder | to display or use the current round information during the game | GameState.java -> getCurrentRound(int currentRound)
TOD-REQ44 | F | the system shall restart the gamestate to its initial values if the players his the "Leave game" button | Stakeholder | to restart the game with a fresh state | GameState.java ->restartGameState()
TOD-REQ45 | F | the system shall allow settign the list of guessed letters into a list and will be displayed towards the players so that they know what letters are at play | Stakeholder | to update the guessed letters during gameplay | GameState.java -> setGuessedLetters(List<String>guessedLetters)
TOD-REQ47 | F | The system shall initialize the game logic with an empty list of Players, a new wordSource and to set the current the current round to 0, everytime a game is about to start | Design Team | to start the game with a known inital state | GameLogic.java -> GameLogic();
TOD-REQ48 | F | the system shall allow adding a player to the game, and updating the logic to affed new players | Stakeholder | to include new players in the game | GameLogic.java -> addPlayers(Player player)
TOD-REQ49 | F | the system shall start the game by settign the currentRound to 1, choosing a new word and starting the round | Stakeholder | to begein gameplay and set inital condidtins for the first round | GameLogic.java -> startGame()
TOD-REQ50 | F | The system shall advance to the next round by incrementing the current round, chooding a new word for the round and start the round | Stakeholder | To proceed wtih the game by moinv on to the next round | GameLogic.java -> advanceRound()
TOD-REQ51 | F | The system shall choose a new word for the game using the WordSource | Stakeholder | to update the word to be guessed for each round | Gamelogic.java -> chooseNewWord()
TOD-REQ52 | F | the system shall allow retrieving the currentword being guessed | Stakeholder | to use the current word in gameplay | GameLogic.java -> getCurrentWord()
TOD-REQ53 | F | the system shall indicate the start of a round with a message printed to the screen | Design Team | to inform players that a new round has started | GameLogic.java -> startRound()
TOD-REQ54 | F | the system shall indicate the end of a round with a message printed to the screen | Design Team | to inform players that a the round has ended | GameLogic.java -> EndRound()
TOD-REQ55 | F | the system shall handle player actions and print a message about the action performed | Stakeholder | to process player actions during the game | GameLogic.java ->playerAction(Player player,String action)
TOD-REQ56 | F | the system shall retrieve the current game state, the current round, current word, and the players score and print them out | Stakeholder | to display the current game state | GameLogic.java -> getGameState()
TOD-REQ57 | F | the system shall allow retrieving the list of players in the game | Stakeholder | to access players information for gameplay and for the server | GameLogic.java-> getPlayers()
TOD-REQ59 | F | the system shall initialize the game server with a emptylist of players and a new instace of GameLogic | Design Team | to start the server with a clean slate and gamelogic ready for use | GameServer.java ->GameServer()
TOD-REQ60 | F | the system shall start the game by invoking startgame from gameLogic and broadcast the gamestate to all players | Stakeholder | to initiate gameplay and to esnsure all of the players are informed of the current game state | GameServer.java -> startGame()
TOD-REQ61 | F | the system shall end the game by printing a message and broadcasting a game end message to all players | Stakeholder | to notify players that the game has ended | GameServer.java -> endGame()
TOD-REQ62 | F | the system shall handle a players action by finding the player by ID, and invoke the player action from gameLogic and brodcast the updated game state | Stakeholder | to process player actions and update all players with the latest game information | GameServer.java -> handlePlayerAction(int playerid ,String action)
TOD-REQ63 | F | the system shall broadcast the current gamestate to all players | Stakeholder | to keep the player updated on the game state | GameSever.java->boradcastGameState(int sessionID)
TOD-REQ64 | F | the system shall add a player to the server and print confirmation message | Stakeholder | to manage players | gameServer.java->addPlayer(Player player)
TOD-REQ65 | F | the system shall remove a player by ID form the server and print confirmation message | Stakeholder | to handle players leaving the game and to update the player list | GameServer.java->removePlayer(int playerid
TOD-REQ66 | F | the system shall provide access to the lsit of players in the server | Stakeholder | to retrive players information | GameSever.java->getPlayer()
TOD-REQ67 | F | the system shall provide access to the current session id | Stakeholder | to identify the current game session | GameServer.java->getSessionId()
TOD-REQ68 | F | the system shall create a new session with a uniwue sesionID and print a confirmation message | Design Team | to initilize anew game with a Unique Identifier | GameServer.java->createSession()
TOD-REQ69 | F | the system shall retrive a player by thier ID from the list of players | Design Team | to manage player-specific actions and updates | Gameserver.java ->getPlayerById(int playerId)
TOD-REQ70 | NF | the systam shall generat a Unique SessionID | Design Team | to ensure each session is unique | GameServer.java ->generateSessionID()
TOD-REQ71 | NF | the system shall broadcast a message to all connected players | Design Team | to makes sure all players retrive the same infomation simultaneously | GameServer.java->broadcastMessage(String message)
TOD-REQ73 | F | the system shall initialize a WebSocket server with the Specified port and Server ID | Design Team | to start the Websocket server with the correct configureations | App.java->App(int port,StringServerId)
TOD-REQ74 | F | the system shall create a GameSession wiht a port that is 100 pors higer thatn the WebSocket port | Design Team | to ensure proper communication and session handling | App.java->App(int port,StringServerId)
TOD-REQ75 | F | the system shall handle new WebSocket connections by incrementing the connection ID, assigning the players to the session and send a connection confirmation messsage | Design Team | to manage player connections and provide feedback | App.java->onOpen(WebScoket conn,ClientHandshake handshake)
TOD-REQ76 | F | the system shall handle WebSocket disconections by removing the playr from the session | Design Team | to manage player disconnections and matain sessions | App.java->onClose(WebSocket conn,int code,String reason,boolean remote)
TOD-REQ77 | F | the system shall process incoming text messages from hte players by passing them to the gameSession for handling | Design Team | to ensure game messages are processed | App.java -> onMessage(Websocket conn, String message)
TOD-REQ78 | NF | the sysrem shall handle errors by printing the stack trace and managing connection -specific error | Design Team | to provide error handling | App.java->onError(Websocket conn,Exception ex)
TOD-REQ79 | F | the system shall start the WebSocket server and initilize the GameSession | Design Team | to set up the server and game session at startUp | App.java->onStart()
TOD-REQ80 | F | the system shall load environment variables for http and WebSocket ports and start both servers | Design Team | to configure the start of the servers using the enviroment setting | App.java->main(Stirng{} args)
TOD-REQ81 | NF | the system shall print status message to indicate the start of both HTTP and WebSocket servers | Design Team | to provide feedback on servers startup | App.java->Main(String[] args)

## TBD LIST
ID | DESCRIPTION | RATIONALE | STATUS / RESOLUTION IDEAS
TBD1 | Procedures for handling player disconnections and reconnections. | To maintain game integrity and player experience, need to determine cases of if a player disconnects after the game has began and also if they were to recconct after that. Would they be allowed to reenter; would their data still be stored? | * Use a grace period to time before they are diconnected and let them know of this when game starts? *Or terminate their score and data upon leaving the session? (If there are only two players the game would need to terminate as well). *Or let them rejoin seamlessly whenever, their turns will be fofeited for as long as they are not in the session, if they rejoin after the game has ended they will be presented with a message showing the final scores fo the session and the winner.
TBD2 | Specific rules for determining winner in case of a tie after additional rounds. | Clarification needed to handle edge cases and rules for them. Will the additional rounds after a tie be sets of 3 rounds like the original game to make it fair for all players? Then if no winners after that set, then another set and so on? | Unresolved
TBD3 | Handling of imcomplete games. | If all players were to diconnect, or if 2 of 4 players dicconect before the game ends does the game still continue for the players remaining in the session? If so, say 1 of the disconnected players has a higher score than the the players still in the session, does the dicsonnected player win or is his data wiped from the scoreboard? Also if all players dicconnect game is over and no winner is determined? | Unresolved
TBD4 | Timing rules for player actions. | Necessary to maintain fairness as well as game pace. Will we equally time players like in the WOF game? Or leave timing to the players? If so what method will be used? | Unresolved