## Task List
Project Requirements
Task | Details | Assigned To | Date Due | Completed By
Use Cases |  | Tyler Crouch | 2024-07-01 | Tyler Crouch
2 Player Game, after start
Join Up nd Game Creation with 2 players
User Interface |  | Noe Sanchez | 2024-07-01 | Noe Sanchez
"Lobby"
"Game"
"Results"
"LeaderBoard / Statistics"
System Requirements |  | Ravi Ray | 2024-07-01 | Ravi Ray
"Lobby"
"Game"
"Results"
"LeaderBoard / Statistics"
|  | Logan Wells | 2024-07-01 | Logan Wells
Unknown List
Review for consistency and completeness
Project Design
Task | Details | Assigned To | Date Due | Completed By
github repository | Invite Team members | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Create branch for Initial Design | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Merge Design Branch | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Set up Repository | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Submitting GitHub Repository | Noe Sanchez | 2024-07-19 | Noe Sanchez
Classs Diagram | Class Player | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Class Websockets | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Class Server | Ravi Ray | 2024-07-19 | Ravi Ray
| Class Scoreboard | Ravi Ray | 2024-07-19 | Ravi Ray
| Class wordsource | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Class WordSelector | Ravi Ray | 2024-07-19 | Ravi Ray
| Class App | Ravi Ray | 2024-07-19 | Ravi Ray
| Class GameServer | Ravi Ray | 2024-07-19 | Ravi Ray
| Class GameState | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Class GameSession | Logan Wells | 2024-07-19 | Logan Wells
| Class GameLogic | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Class HttpServer | Ravi Ray | 2024-07-19 | Ravi Ray
Source Code | ReadMe Description | Logan Wells | 2024-07-19 | Logan Wells
| Implement class Player | Tyler Crouch,Ravi Ray | 2024-07-19 | Tyler Crouch
| Implement class Websockets | Logan Wells | 2024-07-19 | Logan Wells
| Implement class HttpServer | Logan Wells,Ravi Ray | 2024-07-19 | Logan Wells,Ravi Ray
| Implement class GameLogic | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Implement class App | Ravi Ray | 2024-07-19 | Ravi Ray
| Implement class GameServer | Ravi Ray | 2024-07-19 | Ravi Ray
| Implement class GameState | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Implement class WordSelector | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Implement class Scoreboard | Ravi Ray | 2024-07-19 | Ravi Ray
| Implement class GameSession | Logan Wells | 2024-07-19 | Logan Wells
| Implement class WordSource | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Create Main HTMl File | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Set up Initial Js File | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Define Html Structure | Noe Sanchez | 2024-07-19 | Noe Sanchez
| CSS style sections | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Visibillity logic | Noe Sanchez | 2024-07-19 | Noe Sanchez
Requirements | Make requirements for Player class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for Scoreboard class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for Websockets class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for HttpServer class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for GameLogic class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for GameServer class | Ravi Ray | 2024-07-19 | Ravi Ray
| Make requirements for GameState class | Noe Sanchez | 2024-07-19 | Noe Sanchez
| Make requirements for GameSession class | Logan Wells | 2024-07-19 | Logan Wells
| Make requirements for App class | Ravi Ray | 2024-07-19 | Ravi Ray
| Make requirements for WordSource class | Tyler Crouch | 2024-07-19 | Tyler Crouch
| Make requirements for WordSelector class | Tyler Crouch | 2024-07-19 | Tyler Crouch

## Requirements
UID | F/NF | Description | From/Source | Rationale | Implemented by
TOD-REQ01 | NF | The game shall be playable with 2, 3, or 4 players. | Project Description | Ensures flexibility in gameplay to accommodate different numbers of players. | GameSession, Player
TOD-REQ02 | NF | The system shall allow multiple "Turn of Destiny" games to be played simultaneously on the same server. | Project Description | Enables scalability and efficient use of server resources. | App, GameServer
TOD-REQ03 | F | When a player loads the web page, the system shall provide a way to wait for additional players to join. | Project Description | Enhances user experience by managing player waiting time effectively. | GameWebSocket, GameSession, GameServer
TOD-REQ04 | F | The system shall allow the game to start after the second, third, or fourth player joins. | Project Description | Ensures the game can commence once the minimum number of players are present. | GameSession, GameServer
TOD-REQ05 | NF | The game shall be turn-based. | Project Description | Defines the core gameplay mechanic. | GameLogic, Player
TOD-REQ06 | F | The system shall select either one, two, or three words at random from a data file of valid words. | Project Description | Adds variability and challenge to the game. | WordSelector, WordSource
TOD-REQ07 | F | Each word shall be displayed as 'empty cells' to all players, with spaces between words shown. | Project Description | Clarifies word display format for players. | GameLogic, GameSession
TOD-REQ08 | F | The first player to act in a round shall select a button called "Play." | Project Description | Standardizes the starting action for each round. | GameWebSocket, Player
TOD-REQ09 | F | Upon selecting "Play," the game shall select one of 20 possible stakes for the player to win on that turn. | Project Description | Introduces a random reward mechanism to increase excitement. | GameLogic
TOD-REQ10 | F | The system shall display the selected stake to all players, even when it is not their turn. | Project Description | Keeps all players informed and engaged. | GameWebSocket, GameSession, Player
TOD-REQ11 | F | The active player shall decide on an action: solve the puzzle, buy vowels, or select a consonant. | Project Description | Provides clear options for player actions during their turn. | Player
TOD-REQ12 | F | If a player identifies a vowel or consonant, it shall be displayed to all players. | Project Description | Ensures transparency and visibility of game progress. | GameWebSocket, GameSession, Player
TOD-REQ13 | F | The player shall receive the value of the stake for each identified letter, added to their score. | Project Description | Rewards player actions with points. | GameLogic, Player
TOD-REQ14 | F | Players shall take turns in order. | Project Description | Ensures orderly gameplay. | GameLogic, Player
TOD-REQ15 | F | When a player identifies all words, the round shall end. | Project Description | Defines the end condition for each round. | GameLogic, GameSession
TOD-REQ16 | F | A game shall consist of 3 rounds. | Project Description | Establishes the structure of a complete game. | GameLogic, GameSession
TOD-REQ17 | F | At the end of 3 rounds, the player with the largest balance shall be the winner. | Project Description | Determines the winning condition. | GameLogic, GameSession, Scoreboard
TOD-REQ18 | F | If there is a tie, additional rounds shall be played until there is a winner. | Project Description | Ensures a clear winner is determined. | GameLogic, GameSession
TOD-REQ19 | F | The system shall maintain a scoreboard of the highest scoring players from all games played on the server. | Project Description | Provides a competitive element by tracking high scores. | Scoreboard
TOD-REQ20 | NF | The game shall be a client-server system. | Project Description | Defines the architectural model. | GameWebSocket, GameServer
TOD-REQ21 | NF | The user interface shall be a single HTML page, with an optional CSS file. | Project Description | Specifies the simplicity and consistency of the user interface. | HttpHandlerImpl
TOD-REQ22 | NF | All game logic shall be contained in the Java program. | Project Description | Centralizes game logic for maintainability and performance. | GameLogic
TOD-REQ23 | NF | Communications between clients and the server shall be via WebSockets. | Project Description | Ensures real-time, bidirectional communication. | GameWebSocket
TOD-REQ24 | NF | The game shall be hosted on a Linux system. | Project Description | Specifies the operating environment for hosting the game. | App
TOD-REQ25 | NF | The user interface shall have identifiers for each input and output. | Requirements Specification | Facilitates requirement tracking and validation. | HttpHandlerImpl
TOD-REQ26 | F | The system shall provide mockups of the user interface. | Requirements Specification | Helps in visualizing and planning the user interface design. | GameWebSocket, HttpHandlerImpl
TOD-REQ27 | F | The system shall include use cases for joining and creating a game with 2 players. | Requirements Specification | Provides clarity on user interactions and system responses. | GameWebSocket, GameSession
TOD-REQ28 | F | The system shall include use cases for playing a game with 2 players. | Requirements Specification | Defines the flow of gameplay for a minimum player count scenario. | GameWebSocket, GameSession
TOD-REQ29 | NF | The system shall maintain a spreadsheet of system requirements. | Requirements Specification | Ensures organized and systematic requirement documentation. | HttpHandlerImpl
TOD-REQ30 | NF | The spreadsheet shall include columns for F/NF flag, Unique ID, From, Requirement Text, Source, and Rationale. | Requirements Specification | Standardizes requirement documentation for clarity and traceability. | HttpHandlerImpl
TOD-REQ31 | NF | The system shall include a list of unknown or TBD items in an additional tab of the requirements spreadsheet. | Requirements Specification | Manages and tracks ambiguous or unresolved issues. | HttpHandlerImpl
TOD-REQ32 | F | The system shall display the player's score prominently during gameplay. | User Interface | Keeps players informed of their progress and current standing. | GameWebSocket, Player, Scoreboard
TOD-REQ33 | F | The game shall display a timer showing the time elapsed in each round. | User Interface | Adds time pressure and enhances engagement. | GameLogic
TOD-REQ34 | F | The game shall display the current turn's active player. | User Interface | Clearly indicates whose turn it is to all players. | GameWebSocket, Player
TOD-REQ35 | F | The system shall provide a "Forfeit" button for players who wish to quit the game. | User Interface | Allows players to exit the game if they choose to. | GameWebSocket
TOD-REQ36 | F | If a player forfeits, the system shall grant the remaining players a win. | User Interface | Ensures fair play and adjusts the game state accordingly. | GameLogic, GameSession
TOD-REQ37 | F | The system shall deduct a significant penalty from a player's score if they forfeit. | User Interface | Discourages players from quitting the game prematurely. | GameLogic, Player
TOD-REQ38 | NF | The system shall generate a new word puzzle in less than 2 seconds. | Performance Requirement | Ensures a responsive and smooth gameplay experience. | WordSource
TOD-REQ39 | F | The system shall display the correct word puzzle once it is solved. | User Interface | Confirms the correct solution to all players. | GameWebSocket, GameSession
TOD-REQ40 | NF | The system shall log all player actions for audit and analysis purposes. | Logging and Monitoring | Provides a record of gameplay for troubleshooting and performance analysis. | GameWebSocket, HttpHandlerImp
TOD-REQ41 | F | The system shall provide a chat feature for players to communicate during the game. | User Interface | Enhances player interaction and social engagement. | GameWebSocket
TOD-REQ42 | F | The chat feature shall allow toggling between global and local game chat. | User Interface | Provides flexibility in communication options. | GameWebSocket
TOD-REQ43 | F | The system shall save the current game state in case of server issues or disconnections. | Reliability Requirement | Ensures game continuity and resilience. | GameLogic, GameSession, GameServer
TOD-REQ44 | F | The system shall allow players to reconnect and resume their game if they lose connection. | Reliability Requirement | Enhances user experience by allowing recovery from disconnections. | GameLogic, GameSession, GameServer
TOD-REQ45 | NF | The game shall be accessible on all modern web browsers. | Compatibility Requirement | Ensures broad accessibility for users. | HttpHandlerImpl
TOD-REQ46 | NF | The system shall use a secure WebSocket connection (wss://) for communication. | Security Requirement | Protects data integrity and confidentiality during communication. | GameWebSocket
TOD-REQ47 | F | The system shall enforce a turn time limit to keep the game progressing. | Gameplay Mechanic | Maintains game flow and prevents stalling. | GameLogic
TOD-REQ48 | NF | The system shall have automated tests for all major functionalities. | Quality Assurance | Ensures reliability and correctness of the game through continuous testing. | HttpHandlerImpl
TOD-REQ49 | F | The system shall provide visual and sound effects for key game actions (e.g., correct letter, wrong guess). | User Interface | Enhances user experience through feedback and engagement. | GameWebSocket
TOD-REQ50 | F | The system shall allow players to view the scoreboard at any time during the game. | User Interface | Provides ongoing motivation and tracking of progress. | GameWebSocket, Scoreboard
TOD-REQ51 | F | The system should always display the Tiltle of the Game at all time | User Interface |  | GameWebSocket
TOD-REQ52 | F | The Start screen should show the players that are playing in the current game | User Interface | Provides players to view eachother | GameWebSocket
TOD-REQ53 | F | The start screen should have a button to start the game | User Interface | Allows players to enter a game when 2 or more palyers join | GameWebSocket
TOD-REQ54 | F | The rounds screen should have a wheel that sipns and outputs the results of the spin | User Interface | Allows for the players to spin the wheel to get points or to lose a turn | GameWebSocket, GameLogic
TOD-REQ55 | F | The rounds screen should display the remaing words of the alphabet and should be crossed out when its bought and used | User Interface | Allows to all players to see what remaining word are avalible to buy and use. | GameWebSocket, GameLogic
TOD-REQ56 | F | The rounds screen should display the chosen letter | User Interface | Allows for all players to see what current word is being used | GameWebSocket, GameLogic
TOD-REQ57 | F | The rounds screen should have a button that allows for players to buy a letter/vouel | User Interface | Allows for players to the option of selecting a letter to guess and helps progress the game | GameWebSocket
TOD-REQ58 | F | The rounds screen should have a button that allows for players to solve the word(s) | User Interface | Allows the player to solve the word and would keep the game more entertaining | GameWebSocket
TOD-REQ59 | F | The rounds screen should have a button that allows for players to end thier turn | User Interface | Alows for the player to end thier turn, could allow players to skip thier turn. | GameWebSocket
TOD-REQ60 | F | The results screen should display the winner at the top of the rankings | User Interface |  | GameWebSocket, Scoreboard
TOD-REQ61 | F | the results screen should display the losers below the winner | User Interface |  | GameWebSocket, Scoreboard
TOD-REQ62 | F | the results screen should have a button that allows the players to play again | User Interface | Allows for the game to be played by the same players to continue. | GameWebSocket
TOD-REQ63 | F | the results screen should have a button that allows the players to end the game | User Interface | Allows for the game to end so that new players can play. | GameWebSocket
TOD-REQ64 | F | The rounds screen should display the players | User Interface | Allows for players to see how other players are doing, ensures compettition . | GameWebSocket, Player
TOD-REQ65 | F | The Player class shall store the player's name. | Class Player | Allows the game to maintain a record of which player is taking their turn. | Player
TOD-REQ66 | F | The Player class shall keep track of the player's score. | Class Player | Player progress is easily accessed and allows for decision of winner. | Player
TOD-REQ67 | F | The Player class shall indicate whether a player is currently active. | Class Player | Allows for management of player turns and game flow. | Player
TOD-REQ68 | F | The method AddPoints() shall add points to the player's score. | Class Player | It is necessary to update the score to continue the game and decide a winner. | Player
TOD-REQ69 | F | The method resetPoints() shall reset the player's points to zero. | Class Player | It is necessary to reset points before a new round or game. | Player
TOD-REQ70 | F | The method isActivePlayers() shall return the status of a player | Class Player | Ensures correct player is active in the game. | Player
TOD-REQ71 | F | The method setActivePlayers() shall set the active status of a player. | Class Player | Ensures correct player is currently active for their turn. | Player
TOD-REQ72 | F | The method buyVowel() shall process the purchase of a vowel by a player. | Class Player | Players need the ability to choose vowels because most words contain vowels. | Player
TOD-REQ73 | F | The method chooseConsonant() shall process the selection of a consonant | Class Player | Players need the ability to choose consonants because all words contain consonants. | Player
TOD-REQ74 | F | The method solvePuzzle() shall process the player's attempt to solve the puzzle. | Class Player | In order to finish the game, a player must attempt to solve the puzzle | Player
TOD-REQ75 | F | The Scoreboard class shall keep track and sort the player scores. | Class Scoreboard | Ensures correct scores are maintained and shown which allows for accurate winner. | Scoreboard
TOD-REQ76 | F | The GameLogic class shall prompt for player actions. | Class GameLogic | Ensures player actions correspond with the flow of the game. | GameLogic
TOD-REQ77 | F | The App class shall manage multiple WebSocket connections. | Class App | Ensures the server can handle multiple clients simultaneously. | App
TOD-REQ78 | F | The GameLogic class shall manage the state and progression of the game. | Class GameLogic | Centralizes game state management for consistency and maintainability. | GameLogic
TOD-REQ79 | F | The GameServer class shall handle the lifecycle of game sessions. | Class GameServer | Ensures proper management of game sessions from creation to termination. | GameSever
TOD-REQ80 | F | The GameSession class shall handle player actions and game state transitions. | Class GameSession | Facilitates player interaction with the game and manages state changes. | GameSession
TOD-REQ81 | F | The GameState class shall store the current game state, including players and guessed letters. | Class GameState | Maintains a record of the current game state for reference and updates. | GameState
TOD-REQ82 | F | The GameWebSocket class shall manage WebSocket connections and message handling. | Class GameWebSocket | Ensures real-time communication between clients and the server. | GameWebSocket
TOD-REQ83 | F | The HttpHandlerImpl class shall handle HTTP requests and start the WebSocket server. | Class HttpHandlerImpl | Provides an entry point for HTTP requests and initializes WebSocket handling. | HttpHandlerImpl
TOD-REQ84 | F | The Player class shall manage player-specific information and actions. | Class Player | Keeps track of individual player details and their actions during the game. | Player
TOD-REQ85 | F | The Scoreboard class shall maintain and sort player scores. | Class Scoreboard | Ensures accurate tracking and display of player scores. | Scoreboard
TOD-REQ86 | F | The WordSelector class shall select random words for the game from a word source. | Class WordSelector | Adds randomness and challenge by selecting words for the game. | WordSelector
TOD-REQ87 | F | The WordSource class shall read words from a file and provide them for the game. | Class WordSource | Ensures a consistent and valid source of words for gameplay. | WordSource
TOD-REQ88 | F | The GameLogic class shall handle the start and end of game rounds. | Class GameLogic | Manages the transition between different game rounds. | GameLogic
TOD-REQ89 | F | The GameServer class shall broadcast the game state to all connected players. | Class GameServer | Keeps all players updated with the current game state. | GameServer
TOD-REQ90 | F | The GameSession class shall manage the start and end of the game. | Class GameSession | Ensures the proper initiation and termination of the game session. | GameSession
TOD-REQ91 | F | The Player class shall handle the buying of vowels and choosing of consonants. | Class Player | Provides functionality for players to interact with the game puzzle. | Player
TOD-REQ92 | F | The Scoreboard class shall update and sort scores after each player's turn. | Class Scoreboard | Ensures scores are accurately reflected and displayed. | Scoreboard
TOD-REQ93 | F | The App class shall log errors and connection issues. | Class App | Facilitates troubleshooting and monitoring of server performance. | App
TOD-REQ94 | F | The GameLogic class shall choose new words for each round. | Class GameLogic | Adds variety and maintains challenge throughout the game. | GameLogic
TOD-REQ95 | F | The GameWebSocket class shall handle incoming messages and broadcast responses. | Class GameWebSocket | Ensures communication between clients and the server is effective and timely. | GameWebSocket
TOD-REQ96 | F | The GameWebSocket class shall have port and connection fields. | Class GameWebSocket | Ensures correct port number and a websocket connection is made. | GameWebSocket
TOD-REQ97 | F | The GameWebSocket class shall handle any errors. | Class GameWebSocket | Ensures errors are handled smoothly so appropriate actions can be made. | GameWebSocket
TOD-REQ98 | F | The HttpServer class shall start the server. | Class HttpServer | A server is needed to host the game. | HttpServer
TOD-REQ99 | F | The HttpServer class shall check if the server is running. | Class HttpServer | Need to know then server stops working so game can be stopped. | HttpServer
TOD-REQ100
TOD-REQ101

## TBD LIST
ID | DESCRIPTION | RATIONALE | STATUS / RESOLUTION IDEAS
TBD1 | Procedures for handling player disconnections and reconnections. | To maintain game integrity and player experience, need to determine cases of if a player disconnects after the game has began and also if they were to recconct after that. Would they be allowed to reenter; would their data still be stored? | * Use a grace period to time before they are diconnected and let them know of this when game starts? *Or terminate their score and data upon leaving the session? (If there are only two players the game would need to terminate as well). *Or let them rejoin seamlessly whenever, their turns will be fofeited for as long as they are not in the session, if they rejoin after the game has ended they will be presented with a message showing the final scores fo the session and the winner.
TBD2 | Specific rules for determining winner in case of a tie after additional rounds. | Clarification needed to handle edge cases and rules for them. Will the additional rounds after a tie be sets of 3 rounds like the original game to make it fair for all players? Then if no winners after that set, then another set and so on? | Unresolved
TBD3 | Handling of imcomplete games. | If all players were to diconnect, or if 2 of 4 players dicconect before the game ends does the game still continue for the players remaining in the session? If so, say 1 of the disconnected players has a higher score than the the players still in the session, does the dicsonnected player win or is his data wiped from the scoreboard? Also if all players dicconnect game is over and no winner is determined? | Unresolved
TBD4 | Timing rules for player actions. | Necessary to maintain fairness as well as game pace. Will we equally time players like in the WOF game? Or leave timing to the players? If so what method will be used? | Unresolved